## User Stories
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
AUTHENTICATION | Admin | 1.1 register as admin | I can login in the café application | The Admin should not already exsist in the database | All the details provided should be valid | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 2 |  | 2020-05-26 | 2020-06-04 | Completed | Sameer | Done | Given the admin provides the valid credentials,, He will be registered as Admin and redirected to Login page. | Given the admin provides the invalid credentials,, He won't be registered in and a pop up will arise stating that user already exist in the database.
| Customer | 1.2 register as customer | I can login in the café application | The customer should not already exsist in the database | All the details provided should be valid | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) |  |  | 2020-05-26 | 2020-06-04 | Completed |  | Done | Given the customer provides the valid credentials, He will be registered as Customer and redirected to Login page. | Given the customer provides the invalid credentials,, He won't be registered in and a pop up will arise stating that user already exist in the database.
[11 empty] | Completed |  | Writing test cases is remaining
| Admin | 1.3 login as admin | I can view the details and specifications of the café, I can list, update, add and delete the café with the details like name, owner name, location and menu. | The Admin should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 2 |  | 2020-05-27 | 2020-06-04 | Completed |  | Done | Given the admin provides the valid credentials,, He will be logged in and redirected to home page. | Given the admin provides the invalid credentials,, He won't be logged in and a pop up will arise stating about the invalid credentials.
| Customer | 1.4 login as customer | I can get information about the café order from the menu and can give feedback about the menu. | The user should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) |  |  | 2020-05-27 | 2020-06-04 | Completed |  | Done | Given the customer provides the valid credentials, He will be logged in and redirected to home page. | Given the customer provides the invalid credentials,, He won't be logged in and a pop up will arise stating about the invalid credentials.
CAFE MANAGEMENT SYSTEM | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
| Admin | 1.1 Add a new café | I can insert a new cafe with all the details and specifications. | Fields should be of specified format | No field should be null | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 |  | 2020-05-26 |  |  | Shivani | Done | Given : The admin wants to insert a new cafe, when the cafe is not there in the database, then the admin should be able to insert a new café | Given : The admin has to insert a new café, when the cafe is already in the database, then the application will redirect to insert page and display an error message.
|  | 1.2 Update the existing café | I can update the details and specifications of existing café | Fields should be of specified format | No field should be null | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 2 |  | 2020-05-28 |  |  |  | Done | Given : The admin has to update the existing café, when the café is already in the database, then the admin is able to update the existing café. | Given : The admin has to update the existing cafe, when the admin entered the incorrect data, then admin will not be able to update the existing café.
|  | 1.3 View café details | I can view the details and specifications of existing café | The café,s shown should have multiple filters and can be sorted on the basis of specific criteria with pagination | Proper authorization is required/User should be logged in. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 |  | 2020-05-27 |  |  |  | Done | Given : The user has to view the details of the cafe when the cafe already exist in the database, then user should be able to click on view a café. | Given : The user has to view the details of a cafe, when user do not have access to the portal or the data entered is incorrect or the cafe does not exists in the database, then the user will not be able to view the café details.
|  | 1.4 Remove the existing café | I can delete a particular cafe. | Cafe Id/Name entered should be of specified format | Cafe Id/Name should be present in the database. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 |  | 2020-05-26 |  |  |  | Done | Given : The admin has to delete a cafe from database, when the cafe already exist in the database, then admin should be able to click on delete a bus. | Given : The admin has to delete the cafe when admin entered data which has already been deleted from database, then the admin will not be able to delete the cafe
| Customer | 1.5 View café details | I can view the details and specifications of existing café | The café,s shown should have multiple filters and can be sorted on the basis of specific criteria with pagination | Proper authorization is required/User should be logged in. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 |  | 2020-05-27 |  |  |  |  | Given : The admin has to update the existing café, when the café is already in the database, then the admin is able to update the existing café. | Given : The admin has to update the existing cafe, when the admin entered the incorrect data, then admin will not be able to update the existing café.
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
MENU MANAGEMENT SYSTEM | Admin | View Menu Details | Admin can View all the details of the specific Menu. | The Menu Item Details must either have valid Cafeteria ID or Cafeteria Location | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-05-26 | 2020-05-28 | 1. 2. 3. 4. 5. 6. | Neha Tiwari |  | Given the Admin has to view Items in the Menu, he must be able to Click on the View section when it has a valid Cafeteria ID or valid Cafteria location. | Given the Admin has to view the details of the items in the Menu, when the Admin does not have access to the portal or the data entered is incorrect or the item does not exists in the database, then the Admin will not be able to view the items in the Menu.
|  | Add Menu Details | Admin can Add new items in the Menu. | Cafeteria ID must be specified and must not be similar to any existing ID. | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-05-29 | 2020-05-31 | 1. 2. 3. 4. 5. 6. |  |  | Given the admin has to add items to the menu, he must be able to add items when the Cafeteria ID is valid and exists.Also, Item type must contain only characters and Item Price must be a valid Numeric value. | Given the Admin has to add the items in the Menu, when the Admin does not have access to the portal or the Cafeteria ID entered is incorrect or the Item type is not in only character format or the Item Price is not in the valid numeric format, then the Admin will not be able to add the items in the Menu.
|  | Remove Menu Item | Admin can Remove any item from the Menu. | Cafeteria ID or Item ID must exist. | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-06-01 | 2020-06-03 | 1. 2. 3. 4. 5. 6. |  |  | Given the Admin has to remove an item from the Menu, he must be able to Remove the items when the Cafeteria ID or Item ID enteres is valid and exists in the database. | Given the Admin has to remove the items in the Menu, when the Admin does not have access to the portal or the Cafeteria ID or Item ID entered is incorrect , then the Admin will not be able to Remove the item from the Menu.
|  | Update Menu Details | Admin can Update details of any item in the Menu. | The Type or Price of an Item can be updated by using their Item ID or the Cafteria ID that exists. | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1.5 |  | 2020-06-04 | 2020-06-06 | 1. 2. 3. 4. 5. 6. |  |  | Given the Admin has to Update the menu details,he must be able to Update details when the Item ID or Cafeteria ID entered is valid. Also, the update must complete only when Type of the item is Characters only and Price is a Valid Numeric format. | Given the Admin has to Update the details in the Menu, when the Admin does not have access to the portal or the Cafeteria ID or Item ID entered is incorrect , then the Admin will not be able to Update the details in the Menu.The Updated item type must contain only characters and price must be a valid numeric value.
| Customer | View Menu Details | User can View the Menu Items along with their ID, Name and Price. | User must be Logged in. | Item ID or Cafeteria ID must be Valid. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-06-08 | 2020-06-10 | 1. 2. 3. 4. 5. 6. |  |  | Given the Customer wants to View the Menu, he/she must be able to view the Menu details when the Cafeteria ID or the Location of the Cafeteria entered is Valid. | Given the Customer wants to view the Menu Details of the specific Cafteria. If Invalid Cafeteria ID or Location is Entered, then Customer views the message - Wrong Location/Cafeteria ID entered.
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
ORDER MANAGEMENT SYSTEM | Customer | Place Order | Customer can place order | Payment option should be chosen from the dropdown | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (5 hrs) | 2 |  |  |  |  | Snehal Singh |  | The customer must choose the options from menu and can decide the quantity from the drop down provided. A payment option is chosen from the given dropdown and the order is placed. | Trying to order a item that is not in the list. Trying to proceed with the oder without choosing a payment option.
|  | View Order | Customer can view the placed orders using order id | Order is placed | Order Id must be valid | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 | [6 empty] | Given the customer has placed the orders and has the order id. | Given the customer has not placed any order or the order id is invalid
| Admin | View Order | Admin can view the | Valid User Id | User ID must be valid | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 | [6 empty] | Given the admin has the valid user id and gives a specified date | Admin given user Id is invalid
|  | Filter Order | Admin can filter the orders | Filter criteria is applied | Item ID or price range must be Valid. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (5 hrs) | 2 | [6 empty] | Given the Admin wants to filter the orders based on price or item id | The item id given by admin is invalid
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
HELPDESK MANAGEMENT SYSTEM' | Admin | 1.1 view all the queries which are unresolved raised by users | I can view all the queries whose status is unresolved | There should be unresolved queries in the database | No field should be null | 1.Wireframe creation (2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer (1.5 hrs) 7.DAO layer development (1.5 hrs) 8.Controller layer(2 hrs) | 3 |  |  |  |  | Sowrasree |  | Given the admin wants to view all the unresolved queries that are present in the database, then the admin should be able to click on view all the unresolved queries. | Given the admin wants to view all the unresolved queries, When there are no unresolved query in the database, then the application will redirect to previous page and display an error message.
| Admin | 1.2 view all the queries which are resolved | I can view all the queries whose status is resolved | There should be a list of resolved queries in the database. | Bus number should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 | [6 empty] | Given the admin wants to view all the resolved queries that are present in the database, then the admin should be able to click on view all the resolved queries. | Given the admin wants to view all the resolved queries, When there are no resolved query in the database, then the application will redirect to previous page and display an error message.
| Admin | 1.3 Can create a response for a query whose status is unresolved. | I can create a response for a query whose status is unresolved. | The query should be unresolved & There should be an order Id and request in the string form. | Order Id should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 | [6 empty] | Given the admin wants to resolve the unresolved queries that are present in the database, then the admin should be able to click on create response. | Given the admin has to resolve an unresolved query, when admin entered data which has already been resolved, then the admin will not be able to create a response for that query.
| User | 1.4 Can raise a query on an order. | I can raise a query on an order. | There should be an order Id and request in the string form. | Order Id should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 | [6 empty] | Given the user wants to add a new query in the list unresolved queries that are present in the database, then the user should be able to click on raise a query. | Given the user wants to add a new query in the list unresolved queries that are present in the database, and if that order Id is not present in the database then the user will not be able to raise a new query.
| User | 1.5 Can delete a raise a query on an order. | I can delete a raise a query on an order. | There should be an order Id and query in the string form towards that order Id. | Order Id and query should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 | [6 empty] | Given the user wants to delete a query in the list resolved queries that are present in the database, then the user should be able to click on delete query. | Given the user wants to deletea query from the list resolved queries that are present in the database, and if that order Id or the query is not present in the database then the user will not be able to delete query.
| User | 1.5 Can view a response of a query on an order by the Admin. | I can view a response of a query on an order by the Admin. | There should be an order Id ,query and Response in the string form towards that order Id. | Order Id,query and response should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 | [6 empty] | Given the user wants to view a response from the list of responses that are present in the database, then the user should be able to click on view response. | Given the user wants to view a responsefrom the list responses that are present in the database, and if that order Id or the query or the response is not present in the database then the user will not be able to view the response.

## Neha Tiwari
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
MENU MANAGEMENT SYSTEM | Admin | View Menu Details | Admin can View all the details of the specific Menu. | The Menu Item Details must either have valid Cafeteria ID or Cafeteria Location | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-05-26 | 2020-05-28 | 1. 2. 3. 4. 5. 6. | Neha Tiwari |  | Given the Admin has to view Items in the Menu, he must be able to Click on the View section when it has a valid Cafeteria ID or valid Cafteria location. | Given the Admin has to view the details of the items in the Menu, when the Admin does not have access to the portal or the data entered is incorrect or the item does not exists in the database, then the Admin will not be able to view the items in the Menu.
|  | Add Menu Details | Admin can Add new items in the Menu. | Cafeteria ID must be specified and must not be similar to any existing ID. | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-05-29 | 2020-05-31 | 1. 2. 3. 4. 5. 6. |  |  | Given the admin has to add items to the menu, he must be able to add items when the Cafeteria ID is valid and exists.Also, Item type must contain only characters and Item Price must be a valid Numeric value. | Given the Admin has to add the items in the Menu, when the Admin does not have access to the portal or the Cafeteria ID entered is incorrect or the Item type is not in only character format or the Item Price is not in the valid numeric format, then the Admin will not be able to add the items in the Menu.
|  | Remove Menu Item | Admin can Remove any item from the Menu. | Cafeteria ID or Item ID must exist. | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-06-01 | 2020-06-03 | 1. 2. 3. 4. 5. 6. |  |  | Given the Admin has to remove an item from the Menu, he must be able to Remove the items when the Cafeteria ID or Item ID enteres is valid and exists in the database. | Given the Admin has to remove the items in the Menu, when the Admin does not have access to the portal or the Cafeteria ID or Item ID entered is incorrect , then the Admin will not be able to Remove the item from the Menu.
|  | Update Menu Details | Admin can Update details of any item in the Menu. | The Type or Price of an Item can be updated by using their Item ID or the Cafteria ID that exists. | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1 hr) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1.5 |  | 2020-06-04 | 2020-06-06 | 1. 2. 3. 4. 5. 6. |  |  | Given the Admin has to Update the menu details,he must be able to Update details when the Item ID or Cafeteria ID entered is valid. Also, the update must complete only when Type of the item is Characters only and Price is a Valid Numeric format. | Given the Admin has to Update the details in the Menu, when the Admin does not have access to the portal or the Cafeteria ID or Item ID entered is incorrect , then the Admin will not be able to Update the details in the Menu.The Updated item type must contain only characters and price must be a valid numeric value.
| Customer | View Menu Details | User can View the Menu Items along with their ID, Name and Price. | User must be Logged in. | Item ID or Cafeteria ID must be Valid. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1.5 |  | 2020-06-08 | 2020-06-10 | 1. 2. 3. 4. 5. 6. |  |  | Given the Customer wants to View the Menu, he/she must be able to view the Menu details when the Cafeteria ID or the Location of the Cafeteria entered is Valid. | Given the Customer wants to view the Menu Details of the specific Cafteria. If Invalid Cafeteria ID or Location is Entered, then Customer views the message - Wrong Location/Cafeteria ID entered.

## Sowrasree
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
HELPDESK MANAGEMENT SYSTEM' | Admin | 1.1 view all the queries which are unresolved raised by users | I can view all the queries whose status is unresolved | There should be unresolved queries in the database | No field should be null | 1.Wireframe creation (2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer (1.5 hrs) 7.DAO layer development (1.5 hrs) 8.Controller layer(2 hrs) | 2 |  | 2020-05-26 | 2020-06-04 | 1. Done 2. Done 3.Done 4.Done 5.Done 6. Done 7.Done 8. Done | sowrasree |  | Given the admin wants to view all the unresolved queries that are present in the database, then the admin should be able to click on view all the unresolved queries. | Given the admin wants to view all the unresolved queries, When there are no unresolved query in the database, then the application will redirect to previous page and display an error message.
| Admin | 1.2 view all the queries which are resolved | I can view all the queries whose status is resolved | There should be a list of resolved queries in the database. | Bus number should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 |  | 2020-05-26 | 2020-06-04 | 1. Done 2. Done 3.Done 4.Done 5.Done 6. Done 7.Done 8. Done | sowrasree |  | Given the admin wants to view all the resolved queries that are present in the database, then the admin should be able to click on view all the resolved queries. | Given the admin wants to view all the resolved queries, When there are no resolved query in the database, then the application will redirect to previous page and display an error message.
| Admin | 1.3 Can create a response for a query whose status is unresolved. | I can create a response for a query whose status is unresolved. | The query should be unresolved & There should be an order Id and request in the string form. | Order Id should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 |  | 2020-05-27 | 2020-06-04 | 1. Done 2. Done 3.Done 4.Done 5.Done 6. Done 7.Done 8. Done | sowrasree |  | Given the admin wants to resolve the unresolved queries that are present in the database, then the admin should be able to click on create response. | Given the admin has to resolve an unresolved query, when admin entered data which has already been resolved, then the admin will not be able to create a response for that query.
| User | 1.4 Can raise a query on an order. | I can raise a query on an order. | There should be an order Id and request in the string form. | Order Id should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 |  | 2020-05-27 | 2020-06-04 | 1. Done 2. Done 3.Done 4.Done 5.Done 6. Done 7.Done 8. Done | sowrasree |  | Given the user wants to add a new query in the list unresolved queries that are present in the database, then the user should be able to click on raise a query. | Given the user wants to add a new query in the list unresolved queries that are present in the database, and if that order Id is not present in the database then the user will not be able to raise a new query.
| User | 1.5 Can delete a raise a query on an order. | I can delete a raise a query on an order. | There should be an order Id and query in the string form towards that order Id. | Order Id and query should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 |  | 2020-05-28 | 2020-06-06 | 1. Done 2. Done 3.Done 4.Done 5.Done 6. Done 7.Done 8. Done | sowrasree |  | Given the user wants to delete a query in the list resolved queries that are present in the database, then the user should be able to click on delete query. | Given the user wants to deletea query from the list resolved queries that are present in the database, and if that order Id or the query is not present in the database then the user will not be able to delete query.
| User | 1.5 Can view a response of a query on an order by the Admin. | I can view a response of a query on an order by the Admin. | There should be an order Id ,query and Response in the string form towards that order Id. | Order Id,query and response should be present in the database. | 1.Wireframe creation(2 hrs) 2. Writing test cases (2 hrs) 3.DB creation (1 hr) 4. UI design (6 hrs) 5.field validation (3 hrs) 6. Develop service layer(1.5 hrs) 7.DAO layer development(1.5 hrs) 8.Controller layer(2 hrs) | 2 |  | 2020-05-28 | 2020-06-06 | 1. Done 2. Done 3.Done 4.Done 5.Done 6. Done 7.Done 8. Done | sowrasree |  | Given the user wants to view a response from the list of responses that are present in the database, then the user should be able to click on view response. | Given the user wants to view a responsefrom the list responses that are present in the database, and if that order Id or the query or the response is not present in the database then the user will not be able to view the response.

## Sameer Khan
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
AUTHENTICATION | Admin | 1.1 register as admin | I can login in the café application | The Admin should not already exsist in the database | All the details provided should be valid | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 2 |  | 2020-05-26 | 2020-06-04 | Completed | Sameer |  | Given the admin provides the valid credentials,, He will be registered as Admin and redirected to Login page. | Given the admin provides the invalid credentials,, He won't be registered in and a pop up will arise stating that user already exist in the database.
| Customer | 1.2 register as customer | I can login in the café application | The customer should not already exsist in the database | All the details provided should be valid | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) |  |  | 2020-05-26 | 2020-06-04 | Completed |  |  | Given the customer provides the valid credentials, He will be registered as Customer and redirected to Login page. | Given the customer provides the invalid credentials,, He won't be registered in and a pop up will arise stating that user already exist in the database.
| Admin | 1.3 login as admin | I can view the details and specifications of the café, I can list, update, add and delete the café with the details like name, owner name, location and menu. | The Admin should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 2 |  | 2020-05-27 | 2020-06-04 | Completed |  |  | Given the admin provides the valid credentials,, He will be logged in and redirected to home page. | Given the admin provides the invalid credentials,, He won't be logged in and a pop up will arise stating about the invalid credentials.
| Customer | 1.4 login as customer | I can get information about the café order from the menu and can give feedback about the menu. | The user should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) |  |  | 2020-05-27 | 2020-06-04 | Completed |  |  | Given the customer provides the valid credentials, He will be logged in and redirected to home page. | Given the customer provides the invalid credentials,, He won't be logged in and a pop up will arise stating about the invalid credentials.

## Shivam Tewari
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
ORDER MANAGEMENT SYSTEM | Customer | Place Order | Customer can place order | Payment option should be chosen from the dropdown | Proper authorization is required | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (5 hrs) | 2 |  |  |  |  | Snehal Singh |  | The customer must choose the options from menu and can decide the quantity from the drop down provided. A payment option is chosen from the given dropdown and the order is placed. | Trying to order a item that is not in the list. Trying to proceed with the oder without choosing a payment option.
|  | View Order | Customer can view the placed orders using order id | Order is placed | Order Id must be valid | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 | [6 empty] | Given the customer has placed the orders and has the order id. | Given the customer has not placed any order or the order id is invalid
| Admin | View Order | Admin can view the | Valid User Id | User ID must be valid | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (3 hrs) | 1 | [6 empty] | Given the admin has the valid user id and gives a specified date | Admin given user Id is invalid
|  | Filter Order | Admin can filter the orders | Filter criteria is applied | Item ID or price range must be Valid. | 1.Wireframe creation (1 hr) 2. Writing test cases (1.5 hr) 3. UI design (4 hrs) 4. Develop service layer (1.5 hr) 5.DAO layer development (1.5 hr) 6.Controller layer (5 hrs) | 2 | [6 empty] | Given the Admin wants to filter the orders based on price or item id | The item id given by admin is invalid

## Shivani Vishwakarma
Given the Customer wants to view the Menu Details of the specific Cafteria. If Invalid Cafeteria ID or Location is Entered, then Customer views the message - Wrong Location/Cafeteria ID entered. | User Stories
CAFE MANAGEMENT SYSTEM | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
| Admin | 1.1 Add a new café | I can insert a new cafe with all the details and specifications. | Fields should be of specified format | No field should be null |  | 1 |  |  |  | Shivani |  | Given : The admin wants to insert a new cafe, when the cafe is not there in the database, then the admin should be able to insert a new café | Given : The admin has to insert a new café, when the cafe is already in the database, then the application will redirect to insert page and display an error message.
|  | 1.2 Update the existing café | I can update the details and specifications of existing café | Fields should be of specified format | No field should be null |  | 2 | [5 empty] | Given : The admin has to update the existing café, when the café is already in the database, then the admin is able to update the existing café. | Given : The admin has to update the existing cafe, when the admin entered the incorrect data, then admin will not be able to update the existing café.
|  | 1.3 View café details | I can view the details and specifications of existing café | The café,s shown should have multiple filters and can be sorted on the basis of specific criteria with pagination | Proper authorization is required/User should be logged in. |  | 1 | [5 empty] | Given : The user has to view the details of the cafe when the cafe already exist in the database, then user should be able to click on view a café. | Given : The user has to view the details of a cafe, when user do not have access to the portal or the data entered is incorrect or the cafe does not exists in the database, then the user will not be able to view the café details.
|  | 1.4 Remove the existing café | I can delete a particular cafe. | Cafe Id/Name entered should be of specified format | Cafe Id/Name should be present in the database. |  | 1 | [5 empty] | Given : The admin has to delete a cafe from database, when the cafe already exist in the database, then admin should be able to click on delete a bus. | Given : The admin has to delete the cafe when admin entered data which has already been deleted from database, then the admin will not be able to delete the cafe
| Customer | 1.5 View café details | I can view the details and specifications of existing café | The café,s shown should have multiple filters and can be sorted on the basis of specific criteria with pagination | Proper authorization is required/User should be logged in. |  | 1 | [5 empty] | Given : The admin has to update the existing café, when the café is already in the database, then the admin is able to update the existing café. | Given : The admin has to update the existing cafe, when the admin entered the incorrect data, then admin will not be able to update the existing café.

## Snehal TDD Test Cases
TDD Test Cases
Test Case # | Test Case Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Check "View Order" functionality with valid data | 1. Go to site http://localhost:8083/viewOrder 2. Enter Order Id 3. Click on "View" | Order Id: 4002 | The placed order would be displayed
2 | Check "View Order" functionality with invalid data | 1. Go to site http://localhost:8083/viewOrder 2. Enter Order Id 3. Click on "View" | Order Id: 40sd | The order shall not be viewed, "invalid order id" should be shown
3 | Check "Filter Order" functionality with valid data | 1. Go to site http://localhost:8083/filterOrder/item 2. Enter Item Id 3. Click on "Filter" | Item Id: 1002 | The orders with that Item Id should be displayed
4 | Check "Filter Order" functionality with invalid data | 1. Go to site http://localhost:8083/filterOrder/item 2. Enter Item Id 3. Click on "Filter" | Item Id: 111s | No order shall be displayed, "invalid item id" should be shown
5 | Check "payment" functionality with valid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 1234876543657869 expiration date: 08/26 CVV: 444 Full Name on card: Snehal Singh | Transaction should be completed, and the link to download ticket should be displayed
6 | Check "payment" functionality with invalid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 123487657ojf456 expiration date: 08/26 CVV: 444 Full Name on card: Snehal Singh | Transaction should not be completed, "invalid data" should be shown
7 | Check "payment" functionality with invalid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 123487657869 expiration date: 08/26 CVV: 444 Full Name on card: Snehal Singh | Transaction should not be completed, "invalid data" should be shown
8 | Check "payment" functionality with invalid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 1234876543657869 expiration date: 08/18 CVV: 444 Full Name on card: Snehal Singh | Transaction should not be completed, "invalid data" should be shown
9 | Check "payment" functionality with invalid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 1234876543657869 expiration date: 08/26 CVV: 48 Full Name on card: Snehal Singh | Transaction should not be completed, "invalid data" should be shown
10 | Check "payment" functionality with invalid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 1234876543657869 expiration date: 08/26 CVV: 44a Full Name on card: Snehal Singh | Transaction should not be completed, "invalid data" should be shown
11 | Check "payment" functionality with invalid data | 1. Go to site http://localhost:8083/payment 2. Enter card details 3. Click on "complete payment" | card number: 1234876543657869 expiration date: 08/26 CVV: 875 Full Name on card: Sneha1 S1ngh | Transaction should not be completed, "invalid data" should be shown

## Sameer TDD Test Cases
TDD Test Cases
Test Case ID | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Check Admin Login with valid credintials | 1.Go to site http://localhost:8080/login 2.Enter UserId 3.Enter Password 4.Click Login | Userid = Admin101 Password = Admin@123 | Admin should Login into the application
2 | Check Admin Login with invalid credintials | 1.Go to site http://localhost:8080/login 2.Enter UserId 3.Enter Password 4.Click Login | Userid = Admin01 Password = Admin@12 | Admin should not Login into the application
3 | Check Customer Login with valid credintials | 1.Go to site http://localhost:8080/login 2.Enter UserId 3.Enter Password 4.Click Login | Userid = Zoro Password = Zoro@123 | Customer should Login into the application
4 | Check Customer Login with invalid credintials | 1.Go to site http://localhost:8080/login 2.Enter UserId 3.Enter Password 4.Click Login | Userid = Zoro Password = Zoro@12 | Customer should not Login into the application
5 | Check Customer Registration with valid data | 1.Go to site http://localhost:8080/registration 2.Enter User Name 3.Enter Email 4.Enter Phone number 5.Set Password 6.Confirm Password 7.Click Register | User Name= Zoro 3 Email = Zoro@gmail.com Phone Number = 7132343242 Set Password = Zoro@123 Confirm Password = Zoro@123 | Customer should be able to register in the application
6 | Check Customer Registration who is already registered | 1.Go to site http://localhost:8080/registration 2.Enter User Name 3.Enter Email 4.Enter Phone number 5.Set Password 6.Confirm Password 7.Click Register | User Name= Zoro 3 Email = Zoro@gmail.com Phone Number = 7132343242 Set Password = Zoro@123 Confirm Password = Zoro@123 | Customer should not be able to register in the application and a pop will appear stating "customer already exist"
7 | Check Customer Registration with valid data but incomplete fields | 1.Go to site http://localhost:8080/registration 2.Enter UserId 3.Enter Email 4.Enter Phone number 5.Set Password 6.Confirm Password 7.Click Register | User Name= Zoro 3 Email = Zoro@gmail.com Phone Number = Set Password = Zoro@123 Confirm Password = Zoro@123 | Customer should not be able to register in the application
8 | Check Customer Registration with invalid data in email(improper format) | 1.Go to site http://localhost:8080/registration 2.Enter UserId 3.Enter Email 4.Enter Phone number 5.Set Password 6.Confirm Password 7.Click Register | User Name= Zoro 3 Email = Zorogmail.com Phone Number = 7132343242 Set Password = Zoro@123 Confirm Password = Zoro@123 | Customer should not be able to register in the application
9 | Check Customer Registration with invalid data in password(not alphanumeric) | 1.Go to site http://localhost:8080/registration 2.Enter UserId 3.Enter Email 4.Enter Phone number 5.Set Password 6.Confirm Password 7.Click Register | User Name= Zoro 3 Email = Zoro@gmail.com Phone Number = 7132343242 Set Password = 123 Confirm Password = 123 | Customer should not be able to register in the application
10 | Check Customer Registration with invalid data in phone number(not 10 digit) | 1.Go to site http://localhost:8080/registration 2.Enter UserId 3.Enter Email 4.Enter Phone number 5.Set Password 6.Confirm Password 7.Click Register | User Name= Zoro 3 Email = Zoro@gmail.com Phone Number = 7132343 Set Password = Zoro@123 Confirm Password = Zoro@123 | Customer should not be able to register in the application

## Neha TDD Test Cases
Check onward date filter with valid data
Test Case ID | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Check View the Menu with Valid Cafeteria ID | 1. Go to site http://localhost:8080/viewMenu 2. Enter Cafeteria ID 3. Click on search | Cafeteria ID : Cafe01 | Cafeteria having ID "Cafe01" will display its Menu.
2 | Check View the Menu with invalid Cafteria ID | 1. Go to site http://localhost:8080/viewMenu 2. Enter Cafeteria ID 3. Click on search | Cafeteria ID : #24456- | A message "This Café does not Exist!" should be displayed.
3 | Check View the Menu with Valid Cafeteria Location | 1. Go to site http://localhost:8080/viewMenu 2. Enter Cafeteria Location 3. Click on search | Cafteria Location : C Block | Cafteria Menu from Cblock must be displayed.
4 | Check View the Menu with invalid Cafeteria Location | 1. Go to site http://localhost:8080/viewMenu 2. Enter Cafeteria Location 3. Click on search | Cafteria Location : /451! | A message "Enter a Valid Cafeteria Location!" must be displayed.
5 | Check Remove Item from Menu with Valid Data. | 1. Go to site http://localhost:8080/removeItem 2. Enter Item ID 3. Click on Remove | Item ID: 101 | Item having Item ID 101 will be removed from the Menu.
6 | Check Remove Item from Menu with invalid Data. | 1. Go to site http://localhost:8080/removeItem 2. Enter Item ID 3. Click on Remove | Item ID: jhv+ | A message "No Item with this ID exists!" must be displayed.
7 | Check Update Menu with Valid Data | 1. Go to site http://localhost:8080/updateMenu 2. Enter Item ID 3. Input Price and Type 4.Click on Update | Item ID : 101 Type : Tea Price : 10 | The Item having ID 101 will be updated with respective details
8 | Check Update Menu with invalid Data | 1. Go to site http://localhost:8080/updateMenu 2. Enter Item ID 3. Input Price and Type 4.Click on Update | Item ID : 1as Type : T2w Price : A1 | A message "Invalid Input of Data!" must be displayed
9 | Check Add Item with Valid Data | 1. Go to site http://localhost:8080/addItem 2. Enter Cafeteria ID 3. Enter Type 4. Enter Price 5. Click on Add | Cafeteria ID: Cafe01 Type : Coffee Price:10 | The new Item "Coffee" with price Rs.10 will be added to the Cafeteria with ID "Cafe01"
10 | Check Add Item with invalid Data | 1. Go to site http://localhost:8080/addItem 2. Enter Cafeteria ID 3. Enter Type 4. Enter Price 5. Click on Add | Cafeteria ID: 1562# Type : Coffee242 Price:10as | A message "Invalid Input of Data!" must be displayed

## Shivani TDD Test Cases
TDD Test Cases
Test Case # | Test Case Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Enter all the cafe details in the field with valid data | 1. Go to site http://localhost:8081/newCafe 2. Enter cafe details. 3.Click on the button add new cafe | Cafe Name : CgCafe , Café Id : 1001, Location : Mumbai | New cafe will be inserted in database
2 | Enter cafe details with invalid data | 1. Go to site http://localhost:8081/newCafe 2. Enter cafe details. 3.Click on the button add new café | Cafe Name : capgCafe , Café Id : 1001, Location : pune | Error message will be displayed on screen
3 | Check whether the cafe to be deleted is present or not with valid data | 1. Go to site http://localhost:8083/deleteCafe 2. Enter cafe Id 3.Click on the button delete the café | Café Id - 1001 | Cafe data will be deleted from database
4 | Check whether the cafe Id is correct with invalid Id | 1. Go to site http://localhost:8083/deleteCafe 2. Enter cafe Id 3.Click on the button delete the café | Café Id - abc | Error message will be displayed on screen
5 | Check view all cafe details with valid data | 1. Go to site http://localhost:8082/viewCafe 2. Enter name of cafe 3. Click on search | Name of Café : CgCafe | All the café details is viewed
6 | Check view all cafe details with invalid data | 1. Go to site http://localhost:8082/viewCafe 2. Enter name of cafe 3. Click on search | Name of Café : 123 | A message "No cafe found" should be displayed.
7 | Updating the existing café with valid data | 1. Go to site http://localhost:8084/updateCafe 2. Enter cafe details. 3.Click on the button update café | Cafe Name : CG_Cafe , Café Id : 1001, Location : Mumbai | Updated details of existing cafe will be saved in database
8 | Updating the existing café with invalid data | 1. Go to site http://localhost:8084/updateCafe 2. Enter cafe details. 3.Click on the button update café | Cafe Name : cg_Cafe , Café Id : 1001, Location : Mumbai | Error message will be displayed on screen

## Sowrasree TDD Test Cases
TDD Test Cases
Test Case ID | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail
1 | Check "create query" functionality with valid data | 1. Go to site http://localhost:8083/createQuery 2.Enter query for your order in string format. 3. Click on Ok to submit your query. | orderId: 12 Query: late delivery of items | Users query should be submitted and he should be redirected to his page.
2 | Check "create query" functionality with invalid data | 1. Go to site http://localhost:8083/createQuery 2.Enter OrderID and query for your order in string format. 3. Click on Ok to submit your query. | orderId: 21(which doesn't exists) Query: late delivery of items | User should not be redirected to his page, show that data is invalid
3 | Check "create query" functionality with invalid data | 1. Go to site http://localhost:8083/createQuery 2.Enter query for your order in string format. 3. Click on Ok to submit your query. | orderId: 12 Query: A(should contain atleast 20 characters) | User should not be redirected to his page, show that data is invalid
4 | Check "delete query" functionality with valid data | 1. Go to site http://localhost:8083/deleteQuery 2.To delete query for your order, click on delete button next to your query. | orderId: 12 Query: late delivery of items | Users query should be deleted and he should be redirected to his page.
5 | Check "view responses" functionality with valid data | 1. Go to site http://localhost:8080/viewresponses 2. Enter orderId 3. Click on search | orderId: 12 | All responses made by the Admin should be displayed in the respective tab.
6 | Check "view responses" search function with invalid data. | 1. Go to site http://localhost:8080/viewresponses 2. Enter orderId 3. Click on search | orderId: 1234 | A message "No such order" should be displayed.
7 | Check "view queries" with valid data | 1. Go to site http://localhost:8080/viewQueries 2. Enter userName 3. Click on search | userName: Rahul | All the queries of that user should be displayed.
8 | Check "view queries" with valid data | 1. Go to site http://localhost:8080/viewQueries 2. Enter orderItem 3. Click on search | orderItem: orange juice | All the queries of that item should be displayed.
9 | Check "view queries" with valid data | 1. Go to site http://localhost:8080/viewQueries 2. Enter orderId 3. Click on search | orderId: 12 | All the queries of that orderId should be displayed.
10 | Check "view queries" with invalid data. | 1. Go to site http://localhost:8080/viewQueries 2. Enter userName 3. Click on search | userName: RR | A message "No such user" should be displayed.
11 | Check "view queries" with invalid data. | 1. Go to site http://localhost:8080/viewQueries 2. Enter orderItem 3. Click on search | orderItem: orange | A message "No such item" should be displayed.
12 | Check "view queries" with invalid data. | 1. Go to site http://localhost:8080/viewQueries 2. Enter orderId 3. Click on search | orderId: 1234 | A message "No such order" should be displayed.
13 | Check "create response" functionality with valid data | 1. Go to site http://localhost:8083/createResponse 2.Enter response for a query in string format. 3. Click on Ok to submit your response. | orderId: 12 Response: It will be delivered to you in a day. | Users query should be submitted and he should be redirected to his page.
14 | Check "create response" functionality with invalid data | 1. Go to site http://localhost:8083/createResponse 2.Enter response for a query in string format. 3. Click on Ok to submit your response. | orderId: 1234 Response: It will be delivered to you in a day. | A message "No such order" should be displayed.
15 | Check "create response" functionality with invalid data | 1. Go to site http://localhost:8083/createResponse 2.Enter response for a query in string format. 3. Click on Ok to submit your response. | orderId: 12 Response: A(should contain atleast 20 characters). | User should not be redirected to his page, show that data is invalid
16 | Check "view resolvedQueries" with valid data | 1. Go to site http://localhost:8080/ viewResolvedQueries 2. Enter userName 3. Click on search | userName: Rahul | All the resolved queries of that user should be displayed.
17 | Check "view resolvedQueries" with valid data | 1. Go to site http://localhost:8080/ viewResolvedQueries 2. Enter orderItem 3. Click on search | orderItem: orange juice | All the Resolved queries of that item should be displayed.
18 | Check "view resolvedQueries" with valid data | 1. Go to site http://localhost:8080/ viewResolvedQueries 2. Enter orderId 3. Click on search | orderId: 12 | All the Resolved queries of that orderId should be displayed.
19 | Check "view resolvedQueries" with invalid data. | 1. Go to site http://localhost:8080/viewQueries 2. Enter userName 3. Click on search | userName: RR | A message "No such user" should be displayed.
20 | Check "view resolvedQueries" with invalid data. | 1. Go to site http://localhost:8080/viewQueries 2. Enter orderItem 3. Click on search | orderItem: orange | A message "No such item" should be displayed.
21 | Check "view resolvedQueries" with invalid data. | 1. Go to site http://localhost:8080/viewQueries 2. Enter orderId 3. Click on search | orderId: 1234 | A message "No such order" should be displayed.
22 | Check "view all resolved queries" with valid data | 1. Go to site http://localhost:8083/ viewAllResolvedQueries 2.All resolved queries displayed | NA | All the resolved queries should be displayed.
22 | Check "view all unresolved queries" with valid data | 1. Go to site http://localhost:8083/ viewAllUnresolvedQueries 2.All resolved queries displayed | NA | All the unresolved queries should be displayed.